## excel (25)
/No Proyecto/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 112 | 109 | 364
Deleted (D) | 0 | 0 | 38
Modified (M) | 5 | 3 | 49
Added (A) | 93.4 | 77 | 639
Reused (R) | 142 | 163 | 163
Added and Modified (A+M) | 98.4 | 80 | 688
Total Size (T) | 347 | 349 | 1128
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 87 | 77 | 598
Upper Prediction Interval (70%) | 122
Lower Prediction Interval (70%) | 75.4
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 01:36 PM el 1/05/2017